SAAF WORKING GROUP - AALA review for Scottish Government

| Date | Task | Done by | Details |
| --- | --- | --- | --- |
| June 2014 | Decision on plan of action and funding | SAAF working group Scottish Government (SG) | Discussed at 13/6 SAAF meeting SG response to SAAF proposal |
| August/ September 2014 | Book venue, speakers for Oct conference + send out ‘save the date’ emails. | SAAF conference working group |  |
| October 2014 | Officer work on preparation of consultation material, meetings and on-line surveys. | Officer – supervised by SAAF working group + SG secretariat + SG legal |  |
| Late September/ early October 2014 – conference launch | Review of consultation plan and material | SAAF working group. | Discuss SAAF meeting 26/9/ 2014 |
| Late Oct/ early Nov 2014 | SAAF Conference to launch consultation | SAAF working groups |  |
| Conference date until 21st November 2014 | Live on-line surveys, meetings with NGB’s, 4 regional events. Deadline for consultation 21/11. | Officer + SAAF working group + SG secretariat |  |
| 24/11-11/12 | Compile summary of response to consultation | Officer + SG secretariat |  |
| 12/12/14 | Presentation of consultation response to SAAF meeting 12/12/14 | Officer | SAAF discussion to on how to proceed with changes to guidelines. |
| Jan – 13 March 2015 | Draft changes to AALA guidelines | Officer + SG secretariat + SG legal |  |
| 13 March 2015 | 13/3 15 SAAF meeting to review proposed changes to AALA guidelines. | SAAF meeting – attended by Officer + SG legal | SAAF discussion on any further changes to be made. |
| April 2015 | Final changes to AALA guidelines | Officer + SG secretariat + SG legal |  |
| 30/4/15 | Review of AALA guidelines complete. |  |  |